## Test summary report
Tester | HMDao,TTSinh
Date | 2025-06-28
Hạng mục | Số lượng
Number of tested function | 15
Number of test cases | 45
Number of passed test cases | 42
Number of failed test cases | 3

## Bug report
Defect ID | Defect Title | Defect Description | Function ID | Severity | Reported By | Date Reported | Status | Comment
B001 | Unable to open new savings account | System does not create new account even with valid input; no ID returned and no error shown. | UC03 | High | TTSinh | 6/28/2025 | Open | Kiểm tra logic mã sổ
B002 | Wrong interest forecast calculation | Forecast result for 12-month term is incorrect, does not match expected interest rate calculation. | UC09 | Medium | HMDao | 6/28/2025 | Open | Có thể sai công thức tính
B003 | Chatbot not responding | GPT-based chatbot does not reply to any customer query. | UC08 | High | TTSinh | 6/25/2025 | Open | Kiểm tra kết nối API GPT
B004 | Label typo on login button | The label should be “Đăng Nhập” but it appears as “Đăng nhập” (wrong casing). | UC01 | Low | Trần Thanh Sơn | 6/28/2025 | Closed | Đã sửa giao diện
Note on D1: ====== ID#AAABmekwqzw Vu V. Nguyen (2025-06-29 16:23:28) Function ID of the function where the defect is found
Note on E1: ====== ID#AAABmekwqz4 Vu V. Nguyen (2025-06-29 16:23:28) High, Medium, or Low
Note on F1: ====== ID#AAABmekwqz0 Vu V. Nguyen (2025-06-29 16:23:28) Name of the tester who reports the defect
Note on H1: ====== ID#AAABmekwqz8 Vu V. Nguyen (2025-06-29 16:23:28) Open or Closed